## Hometown Pride Monthly Reports_
Hometown Pride Communities | Hometown Pride Coach | Please share your top 3-5 successes from the past month: | Please share 3-5 upcoming events or plans for this month: | What help do you need from Keep Iowa Beautiful or other coaches? | Please upload photos from events discussed in this report | Photo | Photo | Photo | Photo
Dundee, Greeley, Manchester and Ryan | Dan LoBianco | In Manchester: The total raised from a Pizza Ranch fundraiser and group meal included a check from Pizza Ranch for $166.40, plus tips of $781.33. These total $947.73. Also in Manchester two volunteers produced progress being made here signs for various community enrichment improvements being made. In Ryan: The committee finalized the fund it locally list for the ballpark renovation and the got estimates for the major ($100,000) ask of the Major League Baseball/Players Association Foundation ask (New LED Stadium Lighting, Bleachers with cover structure, stormwater maintenance and ADA improvements) and completed the narrative for the letter of intent. In Greeley: Completed the successful Community Souper Bowl Supper community dinner. While a large percentage of the town attended for a team-building success the also raised $1341 to be used for their banner program. | Manchester: A plan for Schram Park 5k/Fun Run/fundraiser: Saturday morning, perhaps 8:00a-Noon, July 6th, was decided, including a themed contest. The contest could involve contribution of dollars = number of votes for the costume contest. “Patriotic Paws" for a pet themed pet/human run. Greeley: Committee to introduce a new historic event in 2024. They will host a side-by-side ride-along and community gathering this fall, taking us on a scenic tour along the three bus routes through and around Greeley, from back in our hay day and as a remembrance of the HOLBERT STALLIONS STABLES" Ryan: Looking at one of the most pride-inducing sites in Ryan. The community is looking at an improvement project for their veteran’s memorial, located across the street from the American Legion Hall downtown. Dundee: Secured bids for phase II of their playground equipment improvement project. | Anxiously looking forward to the presentation by larger companies’ management on “big asks”/sponsorships. | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/03/Group-gathered-at-Pizza-Ranch.jpg
Clinton County HTP | Francis Boggus | 1. Clinton HTP held its first Winterfest on February 2-4th. This well-attended event provided free indoor and outdoor entertainment to allow residents to get out of their homes in mid-winter. 2. On February 16th, the Synergy students from Clinton High toured Iowa State University Innovation + Entrepreneurship School. This trip allowed students to learn how to obtain support for this unique college program. 3. The partnership between Heart & Soul and Clinton Hometown Pride unveiled the Action Plan for Energize Clinton on February 22nd. Over 1,200 participants developed this plan in the last few months. Eight goals were established to energize Clinton and make it an even better place to live, work, and play. 4. The Camanche HTP Committee held a Trivia Night on February 22nd to raise funds for the proposed community splash pad that will break ground this summer. |  | Nothing. | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/03/Synergy-Students-planning-projects-at-CHS-Office.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/03/Synergy-Visit-to-ISU-1.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/03/Synergy-Visit-to-ISU-2.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/03/Synergy-Visit-to-ISU-3.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/03/Camanche-Trivia-Night-1.jpeg
Maquoketa, Peosta, Holy Cross, Rickardsville, Asbury, Sageville | Tricia Wagner | Maquoketa – developed a newsletter to promote HP and eventually help with the last phase of fundraising, the general public. They are tweaking the formatting and intend to roll it out to the public in the next month. I'll share this when they have it finalized. They have also started plans for a public roll out of the project and fundraiser with a website release and ribbon cutting event later this spring. Peosta - the architect presented the first draft of the design for the Kelly Oaks park pavilion and discussed requested modifications with the committee. He is going to bring revised designs to the next meeting. The engineer brought updated trail loop design for the park and everyone approved and agreed to stake it out so the public could walk and see where the trail will go before they take the final plan to city council for approval. Holy Cross - mailed out several funding requests to private foundations to support their mural project, and are submitting the Walmart grant application and possibly the AARP application as well. Asbury - committee discussed various potential projects, and have agreed to move forward with a disc golf course, and a bocce ball court. They also submitted the Paint Iowa Beautiful grant to paint a building using volunteers. Sageville - agreed to plan a visioning session to create a strategic plan to identify projects the community would like to see happen. | Maquoketa – three committee members and myself are going to Des Moines to meet with the program manager for the CAT grant to discuss the Green Space project and application planned to be submitted for next available round of funding. Holy Cross - plan to set up a zoom/teams meeting with the HP committee and the program manager for the Creative Catalyst Project Grant as soon as the NOFO is released to apply for murals. They are also hosting their 2nd Annual Easter Egg Hunt and fundraiser. | n/a
Pocahontas County Hometown Pride Program - February 2024 | Margo Underwood | 1. On Feb. 7th, five Hometown Pride Committees accepted grant awards from the Pocahontas County Foundation for community projects at the Annual Grant Awards Celebration at the Rialto Theatre in Pocahontas. These projects will be completed in 2024 by the Fonda, Gilmore City, Havelock, Rolfe and Varina Hometown Pride Committees. See attached photo and published news story about the Foundation Awards Celebration. 2. Four Hometown Pride Committees applied for Paint Iowa Beautiful Grants: Havelock, Plover, Pocahontas and Varina. 3. City of Pocahontas was selected to host the June 26, 2024 Downtown Forum Meeting by the IEDA Downtown Resources Team. Pocahontas Hometown Pride Committee members will assist the Chamber of Commerce with this meeting. 4. The Fonda Hometown Pride Committee received notification of two additional grants awarded for their School Park Playground Equipment Project from Mid- American Energy and Canadian National Railroad. 5. Varina Hometown Pride Committee has received great raffle prizes for their upcoming fund-raiser on March 17. See attached Poster about this event. | 1. I'm helping with the March 17 Varina Hometown Pride Committee Fund-raiser to raise funds for Handicap accessible sidewalks in Varina's City Park. 2. I'll be presenting a Hometown Pride Program Report at the March 21 Pocahontas County Economic Development Commission Meeting. 3. I'm assisting with a County Trails Committee Meeting this month to update communities about the trail plans underway. 4. I'm preparing proclamations for each community to present during April for Keep Iowa Beautiful Month. 5. Each of the Hometown Pride Committees will have their regular meeting and I plan to participate in each meeting with the Committees. | N/A | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/02/2024-Foundation-Awards-Photo-Large-Group-2-7-24.jpeg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/02/2024-Foundation-Awards-News-Article-in-Laurens-Online-Paper-2-21-24.pdf | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/02/2024-Varina-HP-Fundraiser-Poster.pdf
Center Point, Hills, Shellsburg, Springville, Walker | Jessica Walker | Springville Hometown Pride determined the site location for the community garden project Shellsburg Hometown Pride met with Shellsburg's new mayor and city council to share information about Hometown Pride and work that has been accomplished in the community. We discussed future projects and opportunities for increased collaboration. Shellsburg received IEDA Downtown Walkaround report and recommendations, Hometown Pride was mentioned throughout the report. Many great opportunities and projects to implement! UI's Office of Community Engagement joined the Hills Hometown Pride meeting to present information about their student artist program and the work they do. We are exploring opportunities for collaboration on a mural project, as well as a songbird sanctuary landscape painting project. Walker Hometown Pride booked "All Natural" band on June 1st for the first 2024 Music in the Park event. | Springville Hometown Pride will present plans for a community garden project to City Council. Hills Hometown Pride will meet to determine design, location and potential funding sources for a mural. Walker Hometown Pride will continue planning for 2024 Music in the Park season. | Grant and funding opportunities!
Andrew, Colesburg, Delaware County, Delhi, Edgewood, Hopkinton; Stanwood, West Branch | Marla Quinn\Dawn Danielson | Edgewood - Edgewood is finally zeroing in on a sub-committee for a pool/splash pad project. Delaware County - The trail project is really getting legs (see what I did there?) Only two property owners need to give permission than they plan a town hall meeting, to gage the broader community's support. Delhi - They only have $1,600 left to raise on their pickleball project has real estimates are coming in. Stanwood - Submitted two grant applications: Cedar County Community Foundation to replace Welcome Sign; PIB for city building along Highway 30 West Branch - Lots of opportunity and projects, just need to come up with a plan. We talked to the City Administrator and have some follow up to do. | I don't have any events really that are connected to KIB HP. There may be some that the same committee members are coordinating, but not through KIB HP. | N/A
Worthington | Dylan Michels | • Future planning for mural in town. • Mural artist will be attending our next meeting.
Luxemburg | Dylan Michels | • Applied for RPA 8 TAP Funds for the community trail project. • Planning for future events, including: music in the park and a golf outing. • Welcomed a new member to the committee.
New Vienna | Dylan Michels | • Had our first and second KIB committee meetings. • Narrowed down the projects we would like to focus on first. • More details to come later this year.
Earlville and Delaware | Katie Steffensmeier | Earlville 2 new members Great ideas- possible cleanup day, movie night this summer Passed along a mural artist referral to our committee member. Her dream is to have a mobile coffee truck! Delaware An actual in person meeting with a lot of attendees! Created a flyer and having another fundraiser! | Earlville - Follow-up on clean up day schedule Movie night Explore grant opportunities DCCF Delaware- Develop a group roster Need to solidify OTR grant items Finalize quotes Submit for potential equipment May fundraiser discussion | Any "welcome to the community" things that you do for new residents? What has worked/doesn't? | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/02/2-2024-mural-on-coffee-truck.jpg
Mechanicsville | Jennifer Walker | Scheduled meeting with mayor and city council person to review city's comp plan and IEDA Downtown Walk Around reports, as it had been some time since we reviewed to discuss possible projects for KIB/HP group. One fail: finding a building owner interested in applying for a Catalyst grant. | The full KIB committee will convene in March to discuss new projects. Mechanicsville has a large group of interested citizens, so it's a good time to start planning for the next phases.
Tipton | Jennifer Walker | We have switched gears and I have been working with the Tipton Parks & Recreation Board in recent months as work on the Hardacre Theater has stalled. Together we created an asset map/plan of recreation and wellness opportunities in Tipton, and we have created a vision document of top things the group would like to add in the community. Lots of great ideas! We are working on planning, grants, and installation of new equipment. | The group is working to purchase and install a storybook walk in Tipton City Park and new play equipment. We are discussing "grand opening" events and celebrations, press releases, etc.
Cedar County (CCEDCO) | Jennifer Walker | The leader of this group has been very ill, so we've slowed down quite a lot. Looking for someone else to come in, but also respecting his position. I have scheduled a meeting with the CCEDCO board. | I will meet with the Cedar County Supervisors to discuss Hometown Pride accomplishments and set course for next steps. I am meeting with all of the Cedar County mayors in April to begin planning. Work with Cedar County officials to place Hometown Pride signs.