## Hometown Pride Monthly Reports_
Hometown Pride Communities | Hometown Pride Coach | Please share your top 3-5 successes from the past month: | Please share 3-5 upcoming events or plans for this month: | What help do you need from Keep Iowa Beautiful or other coaches? | Please upload photos from events discussed in this report | Photo | Photo | Photo | Photo | Entry Date
Maquoketa, Asbury, Peosta, Rickardsville, Holy Cross, Sageville | Tricia Wagner | Sageville – recieved a good number of responses to their community survey and most people were in favor of building a community center and park in the open green space. We will discuss at the next meeting. Rickardsville – submitted T-Mobile Hometown Grant to help convert their open air park pavilion into a year round community center. Still working on the Welcome Signs design. Maquoketa – Summer Concert Series/Music on the Green is a big success this year with record turn outs! And fund raising efforts continue. Peosta – Kelly Oaks Park welcome sign design was finalized, selected the playground pour in place colors, and received a presentation by a Boy Scout with his plans for the informational signs through-out Kelly Oaks Park for things like local plants, history of the train, etc. Committee gave feedback and suggestions, but felt his plans were great and right on target! | Maquoketa – plans to write and apply for the CAT grant. Taking/Collecting photos of the KIB signs with committees. |  |  | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/07/XT46628-.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/07/XT46671-.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/07/XT46542-.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/07/XT46570-.jpg | 2024-07-08 11:02
Manchester, Dundee, Greeley & Ryan | Dan LoBianco | • In Ryan: The Ball Park initiative received $1,275 from a Burke Family Memorial fund. Group is working hard to get the name out. • In Manchester: A couple small local retail customer engagement events were held, raising $538.32 at Scooters Coffee and $400 at a round-up at Fareway. • In Greeley: After four years of delays and while a project preceding Hometown Pride Committee work, this committee help land a construction company to finally install the playground equipment that has been in storage since pre-COVID. | • Manchester: There is a “Yoga with your pet” event set for Aug. 10, 7 a.m. at the site of the future dog park. • Greeley: October 26 has been set for a side-by-side car tour of the former bus routes prominent in the heyday of the Major Horse Stables. • Ryan: From an urgency standpoint, there was a small electrical fire (controlled very quickly) on a lights pole in the park, so this has increased the urgency for the lighting improvement project in the committees plan. Visits from two prospective lighting vendors planned in July. • Dundee: Playground equipment should be installed by the end of August. | Updates to the valuable funding database, even more crucial now with some longtime funding sources drying up. | [5 empty] | 2024-07-08 09:01
Center Point, Hills, Shellsburg, Springville, Walker | Jessica Walker | – Shellsburg Hometown Pride completed painting and restoration of the historic Gold Medal Flour Mural! – Artist Shae Hembrey began work on the Landscape Painting/Songbird Project and continued progress on the Songbird Sanctuary Park for Hills Hometown Pride – Hills Hometown Pride had a great turnout for Food Truck Fridays on June 15th & 29th – Shellsburg Hometown Pride Signage and Wayfinding project was approved by city council | – Artist Shae Hembrey will complete the Landscape Painting/Songbird Project for Hills Hometown Pride – Hills Hometown Pride Mural Project artist Bree Neyland will begin painting, pending Iowa Arts Council grant award (fingers crossed!) – Shellsburg Hometown Pride Signage and Wayfinding project implementation | NA | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/07/Song-Bird-Sanctuary-Park-site-6.20.24.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/07/Final-Mural-Restored.jpg |  |  |  | 2024-07-02 14:47
Pocahontas County Hometown Pride Program - June 2024 | Jessica Walker | 1. Gilmore City Hometown Pride Committee Members reviewed the draft of a Community Trails Plan. Working with Stacy Lensch, MIDAS Council of Governments Community Development Director, Hometown Pride Committee members and the public provided suggestions for priority trail corridors to be included in the plan. A photo of the Hometown Pride Committee with Stacy Lensch is included with this report. 2. The City of Pocahontas hosted one of the IEDA Regional Downtown Forums on June 26. Pocahontas Hometown Pride Committee Members welcomed attendees and served as hosts during the event. The program focused on the "Power of the Sign" and provided Best Management Practices for downtown and Wayfinding Signage in communities. Very informative program for communities of all sizes. 3. The City of Rolfe unveiled a new kaleidoscope which was recently installed in Streit Park. Funds to fabricate and install the new kaleidoscope were received from the County Visioning Committee and an Iowa Rural Enrichment Grant. Future plans include installing similar kaleidoscopes in each of the other eight communities in Pocahontas County. The 2023 Inspire Poco Leadership Class participants identified this project as their Legacy Project for Pocahontas County and provided the leadership to implement the project county-wide. A photo of the kaleidoscope dedication is included with this report. | 1. The City of Laurens will be submitting a State Recreational Trail Grant for construction of the next trail corridor northwest of Laurens. This corridor is part of the Laurens Community Trail System. 2. The Varina Hometown Pride Committee is planning a community picnic in the park and raffle fund-raiser on July 28. Funds raised will help support Varina's 125 Celebration in June of 2025. 3. Three communities will host annual summer celebrations in July and Hometown Pride members in Laurens, Rolfe and Pocahontas will be helping with these events in their communities. 4. Fonda Hometown Pride Committee members are continuing the planning process for installing two new pickleball courts in their community. | N/A | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/06/2024-Trail-Planning-Meeting-6-5-24.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/06/2024-Rolfe-Kaleidoscope-Dedication-6-27-24.jpg |  |  |  | 2024-06-29 07:43
Earlville, Delaware | Katie Steffensmeier | Delaware Received funding for last dollar grant! Raised over $1,000 in funds at the town picnic! Got swings ordered for the park! Little Library is FULL of kids and adult books! Great attendance for Fireman's Father's day breakfast! Earlville Had to reschedule spring cleanup due to rain The focus is the 4th of July activities with the Community Club - huge draw to the town First Sunday Farmer's market occurred and was a well attended success | Delaware Plans to apply for mulch and walking trail grant Finalized Phase 2 goals/planning Order covered trellis swings Stake out area in park for swings Developing grant plan for future Earlville Continued mural research Dialog with prolific artist in the area Volunteer Cleanup Hoping to meet after the 4th of July fireworks and volunteer cleanup | Loved Wellmark discussion! | [5 empty] | 2024-06-28 14:59
Luxemburg, New Vienna, and Worthington | Dylan Michels | Luxemburg • Submitted DRA Grant and Dubuque Purchase of Services for Trail Construction funds. • Preparing for our golf tournament fundraiser on July 12th. - Plenty of fun prizes and awards! - Superhero Themed New Vienna • Added a new committee member • Met and discussed projects for next fiscal year - beautification of main street • Meeting again next week Worthington • Submitted application for DRA Core Grant to assist with financing for community mural. • Submitted application for the Iowa Arts Council Arts Project Grant to assist with financing for mural. | Luxemburg • Colesburg Golf Tournament on July 12th for fundraising. Worthington • Will begin purchasing materials next month for mural. | N/A | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/06/Golf-Tournament-Prizes-1.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/06/Golf-Tournament-Prizes-2.jpg |  |  |  | 2024-06-27 17:08
Andrew, Colesburg, Delaware County, Delhi, Edgewood, Hopkinton; Stanwood, West Branch | Marla Quinn | Andrew - Finally agreed to do a Downtown Walkaround and is tentatively scheduled for August! Hopkinton - Is getting a lot of pictures for their photo contest! Edgewood - I have thought of a plan to start over with them and I hope to execute it in July. Long story. | Delhi - Will be incorporating a ribbon cutting for their pickle ball courts project with their Delhi Days event which is July 27th. We are meeting on the format for the ribbon cutting earlier in the month. Hopkinton - Photo contest voting will take place between July 8 and the 19th. Colesburg - Fun and Fireworks is July 6th. (Non HP event) | N/A | [5 empty] | 2024-06-27 16:28
CCEDCO, Tipton, Mechanicsville | Jennifer Walker | - Mechanicsville: - Several meetings of growing committee resulted in Cruse City Park Cleanup Day & Celebration - Committee has decided to focus on expansion of July 4th Celebration. Not sure how much will happen in 2024, but starting to focus on coming years. | For July: - Attend CCEDCO Directors Meeting to share update on KIB/HP - Mechanicsville Cleanup day - Mechanicsville July 4 Celebration | n/a | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2024/06/Jun-28-CleanUpMechanicsville.JPG |  |  |  |  | 2024-06-24 08:58