## hometown-pride-monthly-report-2
Hometown Pride Communities | Hometown Pride Coach | Please share your top 3-5 successes from the past month: | Please share 3-5 upcoming events or plans for this month: | What help do you need from Keep Iowa Beautiful or other coaches? | Please upload photos from events discussed in this report | Photo | Photo | Photo | Photo | Entry Date
Holy Cross, Peosta, Asbury, Maquoketa, Sabula, Sageville | Tricia Wagner | Sabula - the HP committee presented project updates at the March City Council meeting and told the council about the KIB road signs and yard signs on order. They were very receptive! The HP committee has secured a musician for their Kick-off Summer Potluck community event and drafted a survey to send out to the residents and to have available at the community potluck event. Holy Cross - submitted an AARP grant for their pickleball courts and hosted a regional training on the economic benefits of trails and strategies to leverage them. They hope to coordinate with neighboring communities to create a long-range trail plan that will connect them, and potentially to the Heritage Trail. | Sabula - we will finalize the community survey. Holy Cross - holding their third annual easter egg hunt, and preparing the site for the new pickleball courts to be constructed. | na | [5 empty] | 2025-04-07 17:23
Northwest Iowa | Carissa | We have kicked off project planning in all but two communities (Lakeside and Marathon), meaning we have action items laid out and potential funding sources identified for priority projects. I have had great conversations with some key individuals in Buena Vista County. In February I spoke with Justin Yarosevich of BV County Community Foundation about setting up accounts for the Hometown Pride committees. In March all (but two) committees confirmed their interest in having accounts at the Foundation, so have since requested we start that process. Greg Johnson, BV County Conservation was so supportive and excited about the Hometown Pride program. He gave me a lot of tips and resources for working in Buena Vista County. I see some great partnerships brewing, especially if our committee works with the Storm Lake Nature Park project, which Hometown Pride is scheduling a meeting with the City for in April. Lake Park submitted their third grant application for the Silver Lake City Park project - they have a committee member taking that on, and myself and the City Administrator have been reviewing. Sioux Rapids had a productive meeting in March - I wasn't able to attend, so provided guidance in advance. They came out with some solid action items. I am proud of that group. Alta formed a partnership with the schools on a community garden and their clean-up days to expand them to volunteers in the community (in the past it has only been the schools). | Sioux Rapids is setting up a white board at their Fire Department Omelet Breakfast this weekend (April 5th) to get community input and share about Hometown Pride. I have my first meeting with Marathon next week (4/8)! I continue to call Lakeside and hope to get them on the calendar too! At the end of the month Storm Lake HTP will promote their Neighborhood Challenge as a part of Storm Lake Proud Days (May 4-10). They'll ask neighborhoods to post a picture of their neighborhood doing a clean-up effort and one neighborhood will randomly be selected to win a pizza party. A committee member is currently seeking a pizza sponsorship for that. Lake Park is going to start advertising for their Farm to Fork fundraising event being held in June for the Silver Lake City Park project. Three communities plan to submit grant applications to the BV Community Foundation by April 16th: Alta for their community garden, Storm Lake for their downtown benches, and possibly Albert City for playground equipment. | How do the various communities get the word out? I have two Hometown Pride committees interested in a community newsletter - they are wanting this to be something physical to get out to those people who don't have facebook and/or don't receive the paper. Many of these towns don't have a newspaper specifically for their area. If they aren't on social media/don't get the paper, how do they get their news? Do they want the news? I think the concern is there is an underserved population who maybe doesn't have access to those things. | [5 empty] | 2025-04-04 14:03
Delaware County: Dundee, Greeley, Manchester, Ryan. Jackson County: Baldwin & Miles | Dan LoBianco | • In Balwin: Obtain approval from the City Council to go to bid on the new Park Pavilion and other City Park improvements. • In Dundee, Greeley & Ryan: All completed applications to Future Foundationfor Delaware County Grants • In Miles: Completed the first phase of application to the Land & Water Conservation Fund for their splash pad. | • Manchester: Planning for a ribbon cutting/dog ribbon biting, estimated for May to celebrate the Dog Park’s Grand Opening. • In Greeley: Working with a property donation from a former Citizen, now living in Vermont to establish a community garden and possible small band shell. • In Ryan: Committee looking at ways to help (funding?) with restoration project in the Community Cemetery. | [6 empty] | 2025-04-01 19:54
Delaware, Earlville | Katie Steffensmeier | Responses from our fundraising banner/letter! Over $1,000 raised! Research on signage and banners Working on banner design Mid grant report completed | Working to get meetings set up for both Programs this month! Finalizing banner designs and potential signage Fundraising follow-up Hopefully continue discussion of Park Plan for Delaware. Finalize new priorities after phase 1 of the park project. | New fun ideas! Inspiration! | [5 empty] | 2025-04-01 14:10
Clinton County Hometown Pride - March 2025 Report | Francis Boggus | Successes- 1. Lost Nation Hometown Pride received a $2,500 grant from the Lincolnway Foundation for a 4x4 truck. And another $2,500 grant from the Lincolnway Foundation for the Rustic Park playground. 2. Low Moor Hometown Pride received a $2,500 grant for playground equipment for the public park. 3. Camanche Hometown Pride held a public groundbreaking ceremony at Platt Park for the splash pad that will open on Memorial Day weekend on March 27th. 4. Clinton Hometown Pride was able to endow a scholarship fund in recognition of Frederick “Duke Slater” in the amount of $53,000 that will award an annual scholarship to the University of Iowa to a graduating senior from Clinton High. 5. Clinton Hometown Pride was a participant in the first Clinton County Food Insecurity Summit in Clinton on March 27th. Over sixty attendees from the area were registered, including from three additional counties. | Planning – 1. Calamus Hometown Pride applied for the historical museum grant with the Clinton County Development Association. 2. Wheatland Hometown Pride applied for a public park walking path grant with Clinton County Development Association. 3. Calamus Hometown Pride pre- application for the Iowa Economic Development Authority Catalyst grant was approved to move forward to the final round. 4. Calamus and Wheatland Hometown Pride Committees continued planning for the Cal-Wheat Fun Fest in August. |  | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/04/Camanche-HTP-Splash-Pad-Committee-members-with-Community-Coach.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/04/Camanche-Splash-Pad-Groundbreaking-.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/04/Food-Insecurity-Summit-audience-listening-to-keynote-speaker-Emily-Webb.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/04/Food-Insecurity-Summit-Committee-members-in-Clinton.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/04/Food-Security-Summit-flyer-final-2025.png | 2025-04-01 13:11
Center Point, Hills, Shellsburg, Springville, Walker | Jessica Walker | - Obtained updated cost estimates and design options and determined location for Walker Hometown Pride bandshell. - Continued exploring design options for Shellsburg Hometown Pride Mural. - Held successful kick off meeting for Shellsburg Business Association, we had a great turnout! - Finalized lease agreements and confirmed tenants for Springville Community Garden. - Confirmed food trucks for Hills "Food Truck Fridays" | - Planning for Walker Music in the Park June event. - Confirm date and location for second quarterly Shellsburg Business Association meeting. - Set up meeting for Shellsburg Business Association with ECICOG director of environmental services to address recycling issues. - Bring in new dirt and prepping lots for Springville Community Garden. - Kicking off Hills "Food Truck Fridays" on April 23rd! (yes, it's a Wednesday :)) - Holding Songbird Sanctuary Park Dedication Ceremony on Earth Day, April 22nd | Information about grant/funding opportunities for projects. | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/04/Shellsburg-Business-Association-Kick-Off-Meeting-3.18.25.jpg |  |  |  |  | 2025-04-01 09:02
Cedar County, Mechanicsville, Tipton | Jennifer Walker | Cedar County meeting scheduled. It's been quite a while since we've held a meeting in person! Mechanicsville planning for park cleanup. | Uneventful month ahead. | [6 empty] | 2025-04-01 08:17
New Vienna, Worthington and Luxemburg | Dylan Michels | Luxemburg • Successfully completed our Area Wide Scavenger Hunt Event . - Raised $428 - 13 teams of 4-5 people participated • Purchased Information Board to hang in pavilion at the City Park. • Planning for a summer volleyball league in town • Investigating Doggie Waste Post for park New Vienna • Banners – Banners for light posts on Main Street – Secured partial funding through cooperation with another local group and will use as matching funds for grants. • Work continuing for Schaetzles tavern renovations, currently working on reimbursement reports • Working on survey for what people want to see in the community park (repairs, new equipment, fencing, etc.) Worthington • Decorative Light Post Project - City is investing money into building the electrical infrastructure at park - Funds being raised by our committee for the posts and installation - Veteran's Board matching funds spent • Hosted a movie day event for families featuring Matilda • Investigating food truck dinner at some point in summer. | Luxemburg • Bowling Tournament on Saturday, April 12th |  | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/Keep-Luxemburg-Beautiful-Scavenger-Hunt-Flyer-3-18-25.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/KLB-Scavenger-Hunt-Team-Photo.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/KLB-Team-2.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/Keep-Luxemburg-Beautiful-Bowling-Tournament-Flyer-4-12-25.png | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/Worthington-Family-Movie-Day-Poster-3-30-25.png | 2025-03-31 20:36
Andrew, Colesburg, Delaware County, Delhi, Edgewood, Hopkinton, Stanwood, West Branch | Marla Quinn | Hopkinton: The H.O.P.E committee chose a logo. See attached. They also just had their annual spaghetti supper and will finalize plans for the youth bash at the April meeting. Delhi: Submitted a foundation grant for the "Creating a Sense of Place with Entrances" project which involved a new ‘Welcome to Delhi’ sign west of Delhi, and a set of four flower planters at the entrance of the city park, and two at the entrance onto Main St., right across from the city park. Both elements of the project will add new beautification and a sense of welcome to areas where there was nothing before. Also, two new committee members may be added. Colesburg: I hope to get this group going again but they had a personal setback with the main committee member having a brain tumor removed. Their last active project of a new welcome sign finished up in December. | n/a | n/a | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/FinalHOPE_Logo-HiRes.png |  |  |  |  | 2025-03-31 15:41
Pocahontas County Hometown Pride Program - March 2025 | Margo Underwood, Community Coach | 1. The Plover Hometown Pride Committee and Plover Fire Department Leaders worked together with the Pocahontas County Emergency Services Association Coordinator to purchase four new hand-held digital radios for the fire department to use during fire and emergency calls. The radios were presented to the Fire Department earlier this month. 2. All Hometown Pride Committees have received proclamations to present at their April City Council Meetings in conjunction with Keep Iowa Beautiful Month. The Pocahontas County Board of Supervisors will also present and sign a county-wide resolution at their April 1 Supervisor Meeting. 3. The Pocahontas Hometown Pride Committee and Bob Cunningham, Iowa Artist, are collaborating to schedule an Artist Talk during the Pocahontas 155th Celebration in July. The HP Committee will raffle off a signed print of Bob's recent illustration of "Vacationing in Pocahontas" at the conclusion of the Celebration. 4. Gilmore City Hometown Pride Committee and the City of Gilmore City approved design plans for the new shelter house to be built in Sunset Park. A design rendering is included with this report. 5. The Laurens Hometown Pride Committee approved the establishment of the Laurens Community Projects Fund with the Pocahontas County Foundation and the Community Foundation of Greater Des Moines. This new Projects Fund will provide additional funds to help support their future community projects. | 1. Rolfe, Gilmore City, Pocahontas, Fonda, Varina and Laurens Hometown Pride Committees are reaching out to area schools and youth organizations to discuss the Pickup Iowa Program. 2. Community-wide Clean-ups will be scheduled in many of the communities during April and May. The proclamations will be presented at City Council Meetings during April in conjunction with Keep Iowa Beautiful Month. 3. The Varina Hometown Pride Committee is soliciting sponsorships for activities planned during the City's 125 Celebration, June 7-8. | N/A | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/03/2025-Shelter-House-20x36-8000-WPav-Drawing.pdf |  |  |  |  | 2025-03-27 15:02