## hometown-pride-monthly-report-2
Hometown Pride Communities | Hometown Pride Coach | Please share your top 3-5 successes from the past month: | Please share 3-5 upcoming events or plans for this month: | What help do you need from Keep Iowa Beautiful or other coaches? | Please upload photos from events discussed in this report | Photo | Photo | Photo | Photo | Created By (User Id) | Entry Id | Entry Date | Date Updated
Clinton County Hometown Pride | Francis Oliver Boggus | Successes- 1. Wheatland HTP received a grant of $23,300.00 from CCDA for a walking trail around Lions Park. 2. Lost Nation HTP received a $41,300.00 grant from CCDA for a park playground at Gilroy Park. 3. Calamus HTP received $4,000.00 for the remodeling of the Historical Society and Museum at City Hall. 4. Camanche HTP held the ribbon-cutting for the new splash pad built by the City of Camanche and helped with private donations from Hometown Pride. 5. Delmar HTP held its seventh annual free concert in the Historic Railroad Depot area. | Planning- 1. Delmar HTP is planning on finishing the pickleball court that will open by September after having raised over $90,000 for the project. Helped by a generous donor who contributed most of the funding. 2. Lost Nation HTP is planning for the annual Rustic Days for three days of fun from July 18-20th. 3. Low Moor HTP is planning for playground expansion for the community park and veteran’s memorial. 4. Camanche HTP is planning for the purchase of park benches to help landscape the new splash pad in Platt Park | Nothing | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/Camanche-Splash-Pad-Groundbreaking-1.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/Camanche-HTP-Committee-at-New-Splash-Pad1.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/Splash-pad-11.heic | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/Lost-Nation-HTP-Committee-July-8-20251.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/Delmar-with-Francis-Boggus-Community-Coach-July-820251.jpg |  | 11900 | 2025-07-15 20:15 | 2025-07-16 01:15
Albert City, Alta, Aurelia, Lake Park, Lakeside, Marathon, Royal, Sioux Rapids, and Storm Lake | Carissa Harvey | Lake Park HTP held their Farm to Fork event on June 29th with 82 attendees - dollars raised for the Silver Lake City Park project will be reported by the treasurer at their next meeting. We felt it was a successful event - the committee had a lot of fund. They have also received some significant dollar pledges, and were notified of a potential grant award from LWCF (pending federal approval). Storm Lake HTP participated in Kids Fest on June 8th and had a blast - we hosted BINGO. Albert City HTP has been leading concession stands at the baseball fields and reported raising $2,500+ at their last committee meeting, with more events happening. Royal's mural was started by artist Kipp Davis on June 27th. Sioux Rapids HTP attended their City's Council meeting asking for their ok of plans to upgrade the pool park. The Council was very supportive! | Storm Lake HTP will meet with City leaders again to discuss more details for their Nature Park and downtown amenities (starting with benches). Marathon HTP will be approaching the Marathon Poland Park Board with proposed improvements to the park. The NWIA/712 Regional HTP meeting will be held on July 30th. Sioux Rapids will host a fundraising event during Tall Corn Days (July 25-27) Lakeside will hold their first meeting on July 8th. | Nothing at this time. | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/IMG_2542.HEIC | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/IMG_2573.HEIC | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/IMG_2547.HEIC | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/BINGO-PC-City-of-Storm-Lake.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/BINGO.jpg |  | 11893 | 2025-07-08 15:30 | 2025-07-08 20:30
Luxemburg, New Vienna, and Worthington | Dylan Michels | Luxemburg • Planning for 2nd annual golf tournament on July 11th. • Gravel laid for trail and work starting on asphalt New Vienna • Work continuing for Schaetzles tavern renovations and first reimbursement report has been submitted and approved. • Survey for community park and what the community wants results received and discussed with city council (repairs, new equipment, fencing, etc.) - Approval to start a sub-committee for park projects. Worthington • Decorative Light Post Project - Light posts received, electrical work has begun! • Working on recruiting more members | Luxemburg • Coordinating for summer volleyball leagues • Planning for annual golf tournament in July • Planning for Music in the Park event in August New Vienna • Work continuing for Schaetzles tavern renovations • Putting together sub-committee for park equipment |  | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/DJI_0949.JPG | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/DJI_0960.JPG | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/DJI_0954.JPG | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/DJI_0956.JPG | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/DJI_0959.JPG |  | 11887 | 2025-07-03 11:31 | 2025-07-03 16:31
Maquoketa, Sabula, Holy Cross, Peosta, Asbury, Sageville | Tricia Wagner | Maquoketa hosted KIB's Andy and Lorin for a round table discussing the HP and city's accomplishments, and a tour of some of the project sites. This included the green space development, now called Glovik Park. They just poured the foundation for the new stage! Holy Cross hosted KIB's Andy and Lorin for a round table discussing the HP and city's accomplishments, and a tour of the project sites. The committee was awarded a $12,000 AARP grant for the new pickleball courts, and submitted a DRA grant applicatoin which we will learn if awarded on July 22. With this and the anonymous donor, the pickleball courts will be completed later this month! They also submitted a McDonough Foundation grant application for their mural project and will know later this month if awarded. At our June meeting, our committee's secretary who is a Graphic Designer, designed the image for their way-signage and we came up with the list of sites to be included. Sabula held their Community Potluck in the "Park"ing Lot at the fire station and had a good turn out. We collected some more surveys as well. (see photos) Peosta – we created a draft of a brochure/tri-fold fundraising flyer for Kelly Oaks Park development. | Maquoketa planned a new community event, "Dog Days of Summer Fest" August 7th. The Oscar Mayer Wienermobile reached out to them (after attending their Maqtoberfest last year) and asked if they'd like them to make another visit. The committee put the event together in less than a week, with the bulk of it done within a day! In keeping with the Wienermobile theme, they are having Popper Pets canine activities and other events with real dogs, a live band "Dogs on Skis", RC track with an RC Wienermobile toy, plus other treats and kids activities. Holy Cross plans to have the artist for the mural come and stay in one of the committee member's campers the end of July/early August while he paints the mural. They plan to take him for drinks at the brewery one evening, and dinner at one of their local restaurants. The committee's secretary who designed the way-signage image is meeting with a local resident who is going to make the signs and try to get these done this month. The plan is to have these, the mural, and the pickleball courts all done for both their upcoming annual community fundraising event Holy Cross Days on August 9th with parade and street dance, and for the special Field of Dreams Ghost Players event on the ball diamond August 23rd. Sabula – At our June meeting we talked about applying for the Grant for Art Projects and involving high school kids in the painting of the mural that an artist is going to design. We also discussed putting the mural on a weather-proof canvas that can be taken down in the winter and placed inside City Hall. This also helps address the issue with painting directly on the train bridge support surface that is crumbling, and wouldn't last. | n/a | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/bags-3.HEIC | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/dancing-couple-3.HEIC | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/kids-table.JPG | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/overview-of-event.HEIC | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/07/Jenga.HEIC |  | 11884 | 2025-07-01 12:24 | 2025-07-01 17:24
Pocahontas County Hometown Pride Program - June 2025 | Margo Underwood, Community Coach | 1. Varina Hometown Pride Members along with many community volunteers hosted a very successful 125 Anniversary Celebration in Varina on June 7-8. Many activities were held throughout the two-day celebration. It was a memorable event that attracted many visitors from other towns throughout the county too. 2. Rolfe Hometown Pride Committee Members painted the entryway and restrooms in the Rolfe Community Center. The paint was purchased with a grant received from Diamond Vogel Paint and KIB. A photo is attached showing some of the volunteers painting one of the restrooms. 3. Pocahontas Hometown Pride Committee Members worked with Pocahontas Chamber of Commerce volunteers to assemble Welcome Bags for new residents in Pocahontas. | 1. Laurens will be submitting a State Recreational Trail Grant application for construction of a 2.2 mile trail along an abandoned rail corridor northwest of Laurens. 2. Pocahontas will celebrate their 155th Anniversary July 18-20. The Pocahontas Hometown Pride Committee is hosting an Artist Talk with Bob Cunningham, Artist, on July 19, during the Celebration. Committee members are selling raffle tickets to win a signed print by Bob of his art Vacationing at Pocahontas. Bob and his art were featured in the June/July issue of Our Iowa Magazine. I've attached a copy of the article with the print pictured. 3. Plover Hometown Pride will be finalizing their design for new highway signs. 4. Rolfe and Laurens will be hosting town festivals, July 11-13. | N/A | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/2025-PIB-Grant-Photo-Community-Center-Restrooms.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/2025-Vacationing-At-Pocahontas-Picture-in-Our-Iowa-Magazine-June.pdf |  |  |  |  | 11881 | 2025-06-27 14:22 | 2025-06-27 19:22
Center Point, Hills, Shellsburg, Springville, Walker | Jessica Walker | • Held Hills Hometown Pride Mural ribbon cutting/community celebration event June 3rd. • Held Shellsburg recycling meeting with ECICOG Environmental Services June 10th. • Completed Springville Hometown Pride Community Garden planting. • Held Walker Hometown Pride Music in the Park June 14th. | • Plan and hold Shellsburg Business Association quarterly meeting. • Present Walker bandshell project to the Planning & Zoning Commission July 2nd and Walker City Council July 14th. • Continue holding Hills Food Truck Friday events. |  | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/Hills-Mural-Ribbon-Cutting-2.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/Hills-Mural-Ribbon-Cutting-4.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/Hills-Hometown-Pride-Mural-Artist-Drew-Etienne.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/Music-in-the-Park-6.16.25.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/Music-in-the-Park-6.16.25_2.jpg |  | 11880 | 2025-06-26 16:21 | 2025-06-26 21:21
Cedar County, Mechanicsville, Tipton | Jennifer Walker | I met with all of the members of the Tipton KIB committee this month and we went a visited several of the projects they completed this past year, including wind nets for the city pickle ball courts - they had 15 volunteers show up to help hang the nets; the school purchased new soccer nets and installed new bottle fillers; and the day care center was able to raise enough to purchase helmets for the toddlers riding trikes and install a bottle filler. The same day, I met with the Cedar County Conservation naturalist and I was able to visit with her before a summer camp kicked off. She used funds to purchase dip nets and butterfly nets and she had 75 kids and 19 adults use the nets in 4 camps sessions that day! She had been hand sewing the old nets back together, so this was great fun for a lot of folks to get outside and see what they could catch. I met with Mechanicsville's KIB committee mid-month and said, OK, your last year is coming up. What do you want to accomplish and how will we transition off. It was actually pretty rewarding. I thought they'd been idle, but had actually written and received a grant themselves for solar lights for a trail in town. We also talked about some of their beautiful trees in the city park that had to be cut down and the loss of shade at their pavilion. We started working with Outrun the Rays Foundation. Mechanicsville is out of their typical jurisdiction, but they liked the project and invited us to fill out a pre-app. The group is also planning to do their family park day again this year in August. They're interested in building a shade extension on pavilion, possibly a mural, and a sprucing up of the pavilion. | In July several of the communities have Independence Day celebrations. However, at my meeting in Mechanicsville, they shared with me that this is their last one. They have not had great luck increasing their donations for fire works and with the tariffs on China, cannot afford to keep it going. They said even Cedar Rapids has eliminated some of their 4th of July fireworks. Sad, but I get it. |  | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/City-Park-Adam-Pickle.jpg | [5 empty] | 11879 | 2025-06-26 15:46 | 2025-06-26 20:46
Delaware, Earlville | Katie Steffensmeier | Delaware Added fresh mulch to the garden areas We hosted the KIB Picnic in the Park beautiful award ceremony with food truck and desserts. Earlville Held our first meeting in awhile Finalized banner design ideas Working on signage designs | Earlville Finalizing plans for the 4th of July festivities Confirming total funds for project Solifiying banner designs Committing to signage ideas Delaware Ordering picnic tables Ordering trash receptacles Going over grant plan | [7 empty] | 11878 | 2025-06-26 14:56 | 2025-06-26 19:56
Manchester, Ryan, Greeley & Dundee (Delaware County) and Miles & Baldwin (Jackson County) | Dan LoBianco | • In Dundee: New Banners designed and delivered with plenty of lead time for hosting RAGBRAI riders later this summer. • In Miles: Two more successful Community Grillings were held in June and a record setting Tractor Pull all netted nice infusions in the fundraising for the splashpad. Most importantly for Miles, the IRS finally approved and forwarded documents making it official: the Home Town Pride Committee, known as The Miles Community Improvement Club, has achieved 501(c)3 status. • In Greeley: A meeting and bee awareness presentation with ISU extension, Foundation & philanthropic donated land developer was held in June. | • Both Miles (splashpad) & Greeley (Community Garden) are working toward a July 15 application deadline for Walmart Grants. • In Manchester, having opened the Dog Park, the committee turns its focus on downtown building preservation and reuse, as well as a linear park appeal to a necessary daylighting of their City’s east side stormwater system. • In Baldwin: The unfortunate circumstances of a small project and busy construction season resulted in no bids for the new park pavilion construction. Not allowing deflation of their momentum, the committee has new resolve to rebid in November, including a contractor outreach effort, ensuring potential construct through the entire 2026 construction season. The committee also refocused on community furnishings. Looking at benches and tables to freshen public spaces. | [7 empty] | 11877 | 2025-06-25 12:00 | 2025-06-25 17:00
Andrew, Colesburg, Delaware County, Delhi, Edgewood, Hopkinton, Stanwood, West Branch | Marla Quinn | Delhi - The committee is pursuing sidewalks to complete the community and make it walkable. Typically this would be a City initiative, but sometimes, a community group needs to lead a project like this. The City is involved but is not likely to contribute match. Just going by past experience. A new member presented to council a couple of times. She had a map of existing sidewalks and an overlay of proposed sidewalks. The City Council approved the committee to pursue the project. This committee member developed a community survey for the council to approve. Hopkinton took June off from meeting but they are a very engaged and active group. They unveiled the new H.O.P.E. logo at the Civil War Days parade in June. KIB Visit - This was very beneficial for us to visit the other communities. Something that came out of it was that it may be hard for a visitor to find a community's park through Google Maps. You can suggest edits to Google. Communities should try this. We are putting an article in our July newsletter about this. | I don't get involved in the communities' regular events. Some of the communities do things for July 4th. Delhi does Delhi Days at the end of the month. Huge event with a big parade. | n/a | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/20250605_162508.jpg | https://keepiowabeautiful.org/wp-content/uploads/gravity_forms/38-858c04a2763bc85781492a203d7e5488/2025/06/ParadePic.jpeg |  |  |  |  | 11876 | 2025-06-24 10:58 | 2025-06-24 15:58